## Sprint 1 Gantt
Library Management System - Sprint 1 Gantt Chart
Task | Assigned To | Start Date | End Date | Duration (Days) | Status | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21
Sprint 1 Planning | Parshab | 2026-08-10 | 2026-08-10 | 1 | Done | ■
US01 - User Login | Parshab | 2026-08-10 | 2026-08-12 | 3 | Done | ■ | ■ | ■
US02 - Search Books | Parshab | 2026-08-11 | 2026-08-14 | 4 | In Progress |  | ■ | ■ | ■ | ■
US03 - Add Books | Parshab | 2026-08-13 | 2026-08-17 | 5 | Testing |  |  |  | ■ | ■ | ■ | ■ | ■
US04 - Update Book Information | Parshab | 2026-08-15 | 2026-08-18 | 4 | Review | [5 empty] | ■ | ■ | ■ | ■
US05 - Remove Books | Parshab | 2026-08-17 | 2026-08-20 | 4 | Testing | [7 empty] | ■ | ■ | ■ | ■
Sprint Review | Parshab | 2026-08-21 | 2026-08-21 | 1 | Planned | [11 empty] | ■
Sprint Retrospective | All Members | 2026-08-21 | 2026-08-21 | 1 | Planned | [11 empty] | ■

## Sprint 1 Summary
Sprint 1 Summary
Sprint Goal | Establish basic user access and book management functions for the Library Management System.
User Story | Priority | Story Points | Current Status
US01 - User Login | High | 3 | Done
US02 - Search Books | High | 5 | In Progress
US03 - Add Books | High | 5 | Testing
US04 - Update Books Information | High | 8 | Review
US05 - Remove Books | High | 5 | Testing
Total Story Points | 26