## Project Gantt
Library Management System - Project Gantt Chart (Sprint 1 Scope)
# | Phase / Task | Owner | Start Date | End Date | Duration (days) | Status
1 | Requirements Gathering & User Stories | All Members | 2026-08-13 | 2026-08-17 | 4 | In Progress
2 | Trello Board Setup & Backlog | Member 1 | 2026-08-13 | 2026-08-15 | 2 | In Progress
3 | UML Design (Use Case, Class, Sequence, Activity) | Member 2 | 2026-08-16 | 2026-08-22 | 6 | In Progress
4 | GitHub Repo Setup & Structure | Member 2 | 2026-08-16 | 2026-08-18 | 2 | In Progress
5 | Sprint 1 Development | All Members | 2026-08-13 | 2026-08-25 | 12 | In Progress
6 | Feature Branch + Pull Request + Merge | Member 2 | 2026-08-22 | 2026-08-25 | 3 | In Progress
7 | Test Case Design (Unit/Integration/System/UAT) | Member 3 | 2026-08-20 | 2026-08-26 | 6 | In Progress
8 | Test Execution & Test Matrix | Member 3 | 2026-08-26 | 2026-08-29 | 3 | In Progress
9 | Repository Review & Finalization | Member 3 | 2026-08-29 | 2026-08-31 | 2 | In Progress
10 | Screenshots & Final Report Compilation | All Members | 2026-08-30 | 2026-09-02 | 3 | In Progress

## User Story Gantt
Library Management System - Sprint 1 User Story Gantt Chart
ID | User Story | Priority | Points | Start Date | Due Date | Duration (days) | Assignee
1 | US-01: As a member, I want to search the catalog by title, author, or ISBN so I can find books quickly. | High | 3 | 2026-08-13 | 2026-08-15 | 2 | Member A
2 | US-02: As a member, I want to borrow an available book so I can read it. | High | 5 | 2026-08-15 | 2026-08-19 | 4 | Member A
3 | US-03: As a member, I want to return a borrowed book so my account stays in good standing. | High | 3 | 2026-08-17 | 2026-08-20 | 3 | Member B
4 | US-04: As a member, I want to view my borrowing history and due dates so I can avoid late fees. | Medium | 3 | 2026-08-20 | 2026-08-22 | 2 | Member B
5 | US-05: As a librarian, I want to add, edit, or remove books from the catalog so members see accurate information. | High | 5 | 2026-08-20 | 2026-08-25 | 5 | Member C

## Summary
Sprint 1 Summary
Timeline
Today's Date | 08/13/2026
Sprint 1 Start Date | 08/13/2026
Sprint 1 End Date | 08/25/2026
Full Timeline End (incl. testing & wrap-up) | 09/02/2026
Total Duration (days) | 20
Total Phases | 10
Total User Stories | 5
Total Story Points | 19
Phase Status
Status | Phases
Done | 2
In Progress | 3
Not Started | 5
Priority Breakdown
Priority | Stories | Total Points
High | 4 | 16
Medium | 1 | 3
Low | 0 | 0
Workload by Assignee
Assignee | Stories | Total Points
Member A | 2 | 8
Member B | 2 | 6
Member C | 1 | 5
Note
Scope limited to Sprint 1 (Sprint 2 and its backlog items are excluded). Dates stay in sync between the Project Gantt and User Story Gantt sheets.